## Daily Summary
Date | Summary of Work Done | Key Outcomes / Fixes | Issues Filed | Branches / PRs | Notes
2026-09-07 | Dev server crash investigation; fixed SSM registration via NAT gateway rebuild; started building the Codly.ai POC Deployment RunBook. | Root-caused 5 daily reboots to SonarQube autostart + rngd anomaly (manual sudo reboot, not a kernel crash). Fixed dead NAT gateway route restoring SSM on i-0f863fdde75aec22b. Planted 32-step RunBook on staging with real ECR/Docker image references. | — | — | Full crash report published as Artifact.
2026-09-08 | Investigated and fixed two RunBook bugs: OS suggestion field never loading options, and script_runner steps targeting the wrong resource. | OS bug: traced to an 18-month-old dead code path (#2069), but this case's actual cause was a self-inflicted 'Environment=POC' instruction — removed, confirmed fixed live. Resource-mismatch bug: found and fixed a type-string normalization bug in ai_ops_action.py (#2073) — committed to a branch, not yet pushed/PR'd. Cleaned up orphaned test EC2 instance + EBS volume. | #2069, #2073 | fix/runbooks-ai-ops-action-resource-type-mismatch/staging/2026-09-08/2073 (not pushed) | Both issues have detailed root-cause writeups with git blame history.
2026-09-09 | Created a new FlowOps RunBook on prod for EC2 post-deploy automation. | 15-step flow (EBS in matching AZ, IAM role via proven agent, AWS CLI, patching, antivirus, backup, email notification) — reused existing proven agent_hub agents rather than inventing new ones. Created as draft on prod, targeting the AWS Test Account. | — | — | Not yet activated or test-run.