## Daily Tracker
Date | Work Item | Category | Repo | Assigned To | Given By | Time Given | Deadline | Status | Branch Name | Issue Link | PR Link | Source Branch | Notes
2026-09-03 | MSP billing report — backend (aggregator/report/email/celery/manual-trigger endpoint) + frontend dev-mode trigger | Backend+Frontend | Both | obviousom | obviousom |  | 2026-09-03 EOD | In Review | feat/finops-msp-billing-report/staging/2026-09-03/2046 (BE) + feat/finops-billing-dev-trigger/staging/2026-09-03/2046 (FE) | https://github.com/Codly-AI/Codly_Backend/issues/2046 | https://github.com/Codly-AI/Codly_Backend/pull/2048 (backend) ¦ https://github.com/Codly-AI/Codly-Frontend/pull/750 (frontend, after-screenshots pending) | staging | Schedule changed to 1st @ 22:00 IST w/ auto catch-up via ScheduledTrigger ticker (not raw Celery beat). Frontend issue #748 closed/consolidated into backend #2046 per corrected policy (backend-only issues). ¦ Trigger converted to modal w/ editable recipient (default om@allysense.ai for testing); unlock-hint text removed from UI. ¦ Reports redesigned: Excel now Summary sheet + one sheet per customer (account/cloud rollup, no service data); PDF rebuilt as branded cover page + clean rollup table, logo/company pulled dynamically from MSP branding config (tested live: shows real "Agentic AI" branding, not hardcoded Codly). ¦ Switched AWS/Azure/GCP to live cost-manager pulls (no dashboard-snapshot dependency, matches cost_analytics agent tools). Found + fixed 2nd silent-$0 bug class: live calls also swallow real failures (expired Azure secret, deleted Azure subscription) internally; added explicit pre-flight credential/subscription checks since log-capture proved unreliable. Verified live: MSP total $90,192.79, 2 accounts correctly flagged as real failures (broken Azure creds on their end). ¦ FIXED real currency bug: admin_portal migration 0034 (currency_exchange_rate_per_row) was never applied on dev DB -> USD/INR rate silently fell back to 1.0 -> every INR-billed Azure/GCP cost was reported ~95x too high (raw rupees shown as dollars). Applied migration + cleared stale Azure cost cache. TRUE corrected MSP total: $7,577.85 (was $90,192.79 before fix). Previous 2 test emails both had wrong numbers. ¦ Cleaned raw Azure error dumps in email body (JSON/Trace ID stripped to human message). Built Share Log feature (dev-only, ENV startswith("dev")): backend+celery last-10min log bundled as email attachment. Wired frontend Share Log toggle from Coming-soon badge to real Switch. PDF: confidential line no-wrap fix, $ signs added to PDF+Excel (Excel via real currency number_format, not string). ¦ Investigated Share Log on staging/beta/prod (read-only SSM check): backend container has json-file log driver, no docker.sock mount -> app cannot read its own/celery logs from inside container. Real fix needs infra change (CloudWatch shipping recommended over docker.sock mount). Decision: stay dev-only for now. Both PRs opened: BE #2048, FE #750 (FE after-screenshots pending).
2026-09-03 | Waste Mgmt Compute tab: remove all-tier Total Cost KPI, split into Waste/Review/Waste+Review cost tiles, move tier toggle below KPIs | Frontend | Codly-Frontend | obviousom | obviousom |  |  | In Review | fix/waste-mgmt-compute-kpi-tier-toggle/staging/2026-09-03/2049 | https://github.com/Codly-AI/Codly_Backend/issues/2049 | https://github.com/Codly-AI/Codly-Frontend/pull/751 (after-screenshot pending) | staging | Customer dashboard ComputeTab only (src/app/dashboard/finOps/waste-management/page.tsx) - shared TierFilter component untouched, other tabs unaffected. Typecheck clean, 2 pre-existing unrelated errors confirmed via git stash. ¦ Also removed Running Cost KPI (5 tiles now: Total Instances, Waste Cost, Review Cost, Waste+Review Cost, Stopped EBS Cost). Same PR #751 updated.
2026-09-04 | MSP Billing Report — Resource Inventory sheet (count by type + region, all active billed services) | Feature (sub-task) | Codly_Backend | obviousom | sir | 2026-09-04 | EOD 2026-09-04 | In progress — EC2 collector built, live-testing | feat/finops-msp-billing-report-inventory/staging/2026-09-04/2059 | https://github.com/Codly-AI/Codly_Backend/issues/2059 |  | staging | Sub-issue of #2046. Scope widened from EC2/RDS to all billed services per user. Reuses existing waste_management/cost_optimization resource enumeration. Plan: https://claude.ai/code/artifact/6c8d46dd-d648-498b-a455-9633a7422807
2026-09-07 | Fix CookieJWTAuthentication 500 crash on stale/cross-env JWT user_id (prod) — /chatbot/aiops_templates/list/, /admin-api/runbooks/ | Backend / Hotfix | Codly_Backend | obviousom | Manager | 2026-09-07 | ASAP / 2026-09-07 | In Review | hot-fix/auth-jwt-stale-user-crash/main/2026-09-07/2062 | https://github.com/Codly-AI/Codly_Backend/issues/2062 | https://github.com/Codly-AI/Codly_Backend/pull/2063 | main | Root cause: common/authentication.py get_user() raised unhandled User.DoesNotExist on stale/cross-env JWT user_id -> 500 instead of 401. Fixed w/ try/except, verified locally (get_user returns None for nonexistent user_id, no exception). Confirmed live on prod via SSM log check (codly_backend_prod). Also found during investigation: /admin-api/runbooks/run_templates/ 404s on prod — deploy lag only (prod image built 2026-08-17 predates route, beta image 2026-09-04 has it and returns 200), not a code bug, no PR — needs prod redeploy from main, flagged to team separately.
2026-09-07 | Dev server (i-070fa60ad49785f8d) crash investigation — 5 hard reboots in one day | Infra/DevOps | N/A (EC2 infra) | obviousom | obviousom |  |  | Diagnosed — fix (disable SonarQube autostart) not yet applied |  |  |  |  | Root cause: SonarQube's 3-JVM stack auto-starts on every boot and burns ~295% CPU within 60s (of 400% available), plus anomalous rngd at 106% CPU. Memory/swap thrash makes the box unusably slow; confirmed via auth.log it's a manual `sudo reboot` by user3 each time, not a kernel panic or OOM-kill. Full report: https://claude.ai/code/artifact/6f83e337-12bc-4933-85fc-8bcc-f61111d029d0
2026-09-07 | Fixed SSM registration failure for i-0f863fdde75aec22b (AWS Test Account 299372338199) — dead NAT gateway route | Infra/AWS | N/A (AWS infra) | obviousom | obviousom |  |  | Fixed & verified live |  |  |  |  | Route table rtb-04d5865769450de0a's 0.0.0.0/0 route pointed at a deleted NAT gateway. Provisioned nat-04a7e36024427e5e9 + new EIP, replaced the route. Instance registered with SSM ~4 min later (PingStatus: Online confirmed). Left running per user — ongoing ~$0.05/hr cost.
2026-09-07/08 | Built + tested 'Codly.ai POC Deployment RunBook' (32-33 step EC2 + Docker app-stack flow) | Backend/RunBooks | Codly_Backend | obviousom | obviousom |  |  | Built, iteratively tested; execution bugs found (see below rows) |  |  |  | staging | Planted on staging (dc111fb7-bb0e-4d70-9e79-3f0b33f75158) and local dev (cb366650-...). Real ECR/Docker Hub images resolved live (codly_backend:staging, codly_frontend:staging-latest, codly_db:prod_05_march-20260827-114721 — corrected after an initial wrong mysql:8 guess). codly_backend ECR repo found to have 0 tagged images (separate flag). Hit Azure OpenAI gpt-5.4 429 rate limiting from repeated same-day testing — quota issue, not a bug.
2026-09-08 | OS suggestion field never loads options in AI Ops / RunBook dynamic forms | Backend/Bug | Codly_Backend | obviousom | obviousom |  |  | Root cause found + corrected mid-investigation; narrow fix applied, broader fix not merged |  | https://github.com/Codly-AI/Codly_Backend/issues/2069 |  | staging | git blame traced the flawed 'OS tag on AMIs' strategy to the file's original 2025-03-04 commit (5 commits/4 authors since, none fixed it). Live testing then proved the actual trigger for THIS case was self-inflicted: a RunBook instruction I wrote ('Environment=POC') with no matching tagged AMI in the account — removing that instruction fixed it, matching AI Ops chat's own successful 'Environment=Production' result exactly. Broader fragility (the mechanism only works if someone manually tags an AMI) is still real, tracked in #2069; a real-AMI-catalog code fix was drafted then intentionally reverted as unnecessary for now.
2026-09-08 | RunBook script_runner steps target wrong resource (EBS volume ID instead of EC2 instance ID) | Backend/Bug | Codly_Backend | obviousom | obviousom |  |  | Fix committed on branch — NOT pushed, no PR yet | fix/runbooks-ai-ops-action-resource-type-mismatch/staging/2026-09-08/2073 | https://github.com/Codly-AI/Codly_Backend/issues/2073 |  | staging | Root cause: ai_ops_action.py stored the AI's CloudFormation-style type string ('AWS::EC2::Instance') verbatim, never matching RunContext.get_resource_id()'s exact 'ec2_instance' check — so a later EBS-volume-creating step silently clobbered the fallback instance_id, and every script_runner step after it targeted the volume instead of the instance. Confirmed live on staging run ea6407a2-.... Fix normalizes the type string at write time (1-file, 13-line diff). Terminated the orphaned test EC2 instance (i-0f140f0daa3b6c454) + EBS volume (vol-0bd4fbea95f53ad58) created during reproduction, with user approval.
2026-09-09 | New RunBook created on PROD: 'EC2 Post-Deploy: Storage, IAM, Patch & Backup' (FlowOps) | Backend/RunBooks | Codly_Backend | obviousom | obviousom |  |  | Created (draft), not yet activated/tested |  |  |  |  | 15-step flow: wait -> check AZ (read-only) -> create+attach EBS in same AZ -> create+attach IAM role (reusing the proven 'Executor Node'/power_access agent from the existing 'Post Ec2 workflow for deployment') -> install AWS CLI v2 -> check internet -> Patching Agent (id=13) -> Install Antivirus (id=14) -> backup (built-in agent) -> email vishal@allysense.ai via SES (from info@codly.ai). Triggers: manual + ai_ops_resource_created(create_ec2). Targets AWS Test Account (299372338199) per explicit user choice among 3 candidate accounts on prod.
2026-09-09 | Budget & Chargeback cost-distribution fixes: MySQL conditional-unique-constraint gap (BudgetAccounts/TagBudget dup risk) + missing FIXED_PERCENTAGE/FIXED_VALUE reconciliation check (BE) + Increased Cost column markup label (FE) | Backend+Frontend | Both | obviousom | Vishal | 2026-09-09 | ASAP / 2026-09-09 | Branch created — starting fix | fix/budget-chargeback-distribution-integrity/staging/2026-09-09/2079 (BE) + fix/budget-chargeback-increased-cost-label/staging/2026-09-09/2080 (FE) | https://github.com/Codly-AI/Codly_Backend/issues/2078 (parent) ¦ https://github.com/Codly-AI/Codly_Backend/issues/2079 (BE) ¦ https://github.com/Codly-AI/Codly_Backend/issues/2080 (FE) |  | staging | Found during staging cost-distribution investigation, logged in documentation and logging/expectation/feature - budget management.MD. Verified live on staging (read-only): no active data corruption yet, both are latent/defense-in-depth gaps.
2026-09-09 | Tag-wise chargeback report: add account selection (Account Selection checkboxes were decorative/disabled, now functional; selection threaded through cost-fetch, RI/SP-fetch, report payload) | Frontend | Codly-Frontend | obviousom | Vishal | 2026-09-09 | ASAP / 2026-09-09 | FE implemented, typecheck clean (no ChargebackForm errors) — pending live UI verification | fix/budget-chargeback-increased-cost-label/beta/2026-09-09/2080 | https://github.com/Codly-AI/Codly_Backend/issues/2081 (parent: Budget issue) ¦ https://github.com/Codly-AI/Codly_Backend/issues/2082 (sub-issue) |  | beta | Corrected branch base 2026-09-09: initially cut from staging by mistake, recreated from beta for both BE and FE (stash + recheckout, no work lost). No backend change needed for this feature - create_chargeback_tag already only persists whatever tags_info rows are submitted, so excluding an account client-side is sufficient.
2026-09-15 | Budget Tracker: account-budget wizard parity, per-account/tag alert-email editing on existing budgets, Budget & Chargeback landing page card-grid redesign | Backend+Frontend | Both | obviousom | obviousom |  |  | In Review — after-screenshots pending | fix/budget-chargeback-distribution-integrity/beta/2026-09-09/2079 (BE) + fix/budget-chargeback-increased-cost-label/beta/2026-09-09/2080 (FE) | https://github.com/Codly-AI/Codly_Backend/issues/2097 | https://github.com/Codly-AI/Codly_Backend/pull/2098 (backend) ¦ https://github.com/Codly-AI/Codly-Frontend/pull/773 (frontend, after-screenshots pending) | staging | Real backend bug found+fixed: AccountBudgetSerializer.create() forced every alert-email entry's account_ids to the full account list, ignoring per-entry scoping - live-verified fix via PATCH + DB read on real test budgets #24/#25. Frontend: account-budget wizard brought to parity with tag-budget wizard (per-account picker, derived-editable Amount, shared trend chart, unified Step 2/9/11 layout); new EditBudgetAlertsDialog lets thresholds/notification emails be edited on an already-created budget; landing page rebuilt as a real card grid (search box wired to a param/store that already existed but was never connected) with a much richer expand view (usage gauge w/ threshold ticks, monthly trend, breakdown donut, threshold ruler, Yearly-budget pacing view). Chargeback tab untouched (diff-verified). Before screenshot real (user-supplied, saved under pr-evidence/2097-budget-landing-redesign/); after-screenshots blocked on browser login (can't type password per hard rule) - flagged to @obviousom in the PR to capture and attach before merge.